## Social Media Module
Social Media Module — Feature Completion & Delivery Schedule
Standalone module plan • Target timeline: 2 months
Module | Section / Category | Feature | Mobile % | Mobile Status | Backend % | Backend Status | Plain-English Notes | Days to Finish | Section (filled) | Work Days (numeric)
SOCIAL MEDIA
SOCIAL MEDIA | User Account & Profile | Sign Up & Login (Email, Phone, Google) | 90% | Complete | 90% | Complete | Login and registration fully work across all three methods. | Done | User Account & Profile | 0
|  | Two-Factor Authentication (extra login security) | 0% | Not started | 0% | Not started | Not built yet. Users have no second step for securing their account. | 3 working days | User Account & Profile | 3
|  | Profile Picture Upload | 90% | Complete | 90% | Complete | Users can upload and update their profile photo. | Done | User Account & Profile | 0
|  | Bio, Gender, Location & Birthday | 80% | Complete | 80% | Complete | Profile info screen works. Minor tweaks needed. | 1 working day | User Account & Profile | 1
|  | User Interests & Hobbies Selection | 80% | Complete | 80% | Complete | Interest selection after sign-up is done. | 1 working day | User Account & Profile | 1
|  | Follow / Unfollow & Friends System | 80% | Complete | 80% | Complete | Following and followers work. Small polish needed. | 1 working day | User Account & Profile | 1
|  | Verified Badge (blue tick) | 30% | In progress | 40% | In progress | Badge exists but the full verification process is not complete. | 3 working days | User Account & Profile | 3
|  | Privacy Settings (public, private, custom) | 0% | Not started | 20% | Just started | Privacy screen does not exist in the app yet. | 4 working days | User Account & Profile | 4
|  | Block & Report Users | 40% | In progress | 50% | In progress | Buttons exist but the full block/report flow needs finishing. | 2 working days | User Account & Profile | 2
|  | Profile QR Code | 0% | Not started | 0% | Not started | Not built. Users cannot share their profile via QR code. | Post-Launch | User Account & Profile | 0
| Social Feed (Timeline) | Scrolling Home Feed | 85% | Complete | 80% | Complete | Main home feed works well. Users can scroll through posts. | Done | Social Feed (Timeline) | 0
|  | Image Posts | 85% | Complete | 80% | Complete | Image posts in the feed are fully working. | Done | Social Feed (Timeline) | 0
|  | Video Posts | 80% | Complete | 75% | Mostly done | Video posts display and play correctly. Minor improvements needed. | 1 working day | Social Feed (Timeline) | 1
|  | Text / Status Posts | 80% | Complete | 75% | Mostly done | Text-only posts work in the feed. | 1 working day | Social Feed (Timeline) | 1
|  | Story Feed (24-hour content) | 75% | Mostly done | 70% | Mostly done | Story bar at top of feed works. | 1 working day | Social Feed (Timeline) | 1
|  | Reels / Short Videos | 80% | Complete | 75% | Mostly done | Short video reels screen works. | 1 working day | Social Feed (Timeline) | 1
|  | Carousels (multiple photos in one post) | 60% | Mostly done | 60% | Mostly done | Multi-image posts exist but the swipe experience needs work. | 3 working days | Social Feed (Timeline) | 3
|  | Polls in Posts | 0% | Not started | 0% | Not started | Not built. Users cannot create polls. | 3 working days | Social Feed (Timeline) | 3
|  | Check-Ins & Location Tagging | 20% | Just started | 20% | Just started | Started but location cannot be tagged on posts yet. | 3 working days | Social Feed (Timeline) | 3
|  | Tag Friends in Posts | 40% | In progress | 40% | In progress | Tagging works partially. Needs completion. | 3 working days | Social Feed (Timeline) | 3
|  | Hashtags | 50% | In progress | 50% | In progress | Hashtags display but searching by hashtag is incomplete. | 2 working days | Social Feed (Timeline) | 2
|  | Trending Section | 20% | Just started | 30% | In progress | Not working yet. No trending topics or content shown. | 4 working days | Social Feed (Timeline) | 4
|  | "For You" Personalised Feed | 0% | Not started | 0% | Not started | Not built. Requires a recommendation system to be developed. | 8 working days | Social Feed (Timeline) | 8
|  | Recommended Users & Posts | 20% | Just started | 20% | Just started | Very basic suggestions. Needs proper logic. | 3 working days | Social Feed (Timeline) | 3
| Posting & Content Creation | Take Photo or Video from App Camera | 85% | Complete | 80% | Complete | Camera capture for posts and stories works. | Done | Posting & Content Creation | 0
|  | Camera Filters & Beauty Effects | 25% | Just started | 20% | Just started | Very early stage. Proper AR filters not done yet. | 7 working days | Posting & Content Creation | 7
|  | Upload Multiple Photos / Videos | 80% | Complete | 75% | Mostly done | Multiple file upload works. | 1 working day | Posting & Content Creation | 1
|  | Save Post as Draft | 30% | In progress | 40% | In progress | Draft saving is unreliable. Needs fixing. | 2 working days | Posting & Content Creation | 2
|  | Edit or Delete a Post | 60% | Mostly done | 65% | Mostly done | Delete works. Post editing needs to be completed. | 2 working days | Posting & Content Creation | 2
|  | Captions with Emojis | 75% | Mostly done | 70% | Mostly done | Caption input with emoji picker works. | 1 working day | Posting & Content Creation | 1
|  | Add Music to Videos or Stories | 65% | Mostly done | 60% | Mostly done | Music can be added. Library is limited. | 2 working days | Posting & Content Creation | 2
|  | AI Auto-Caption Suggestion | 0% | Not started | 0% | Not started | Not built. Would require AI integration. | Post-Launch | Posting & Content Creation | 0
|  | Start a Live Stream | 65% | Mostly done | 65% | Mostly done | Going live works using the Agora system. | 2 working days | Posting & Content Creation | 2
|  | Co-Host a Live Stream | 50% | In progress | 55% | In progress | Co-host invite screen exists but the full flow is incomplete. | 3 working days | Posting & Content Creation | 3
|  | Viewers Join Live as a Guest | 50% | In progress | 55% | In progress | Guest joining is partially done. | 3 working days | Posting & Content Creation | 3
|  | Send Gift Coins During Live | 55% | In progress | 60% | Mostly done | Coin gifting partially works during live streams. | 2 working days | Posting & Content Creation | 2
| Engagement | Like & React to Posts | 80% | Complete | 75% | Mostly done | Likes and emoji reactions on posts work. | 1 working day | Engagement | 1
|  | Comment on Posts | 80% | Complete | 75% | Mostly done | Users can comment on posts. | 1 working day | Engagement | 1
|  | Reply to Comments (threaded) | 60% | Mostly done | 60% | Mostly done | Replies partially work. Threading needs improvement. | 2 working days | Engagement | 2
|  | Heart / Favourite a Comment | 40% | In progress | 45% | In progress | Button exists but saving does not always work. | 1 working day | Engagement | 1
|  | Share Posts | 60% | Mostly done | 55% | In progress | Sharing within app is partial. Sharing to other apps needs work. | 2 working days | Engagement | 2
|  | Save / Bookmark Posts | 70% | Mostly done | 70% | Mostly done | Users can save posts. Saved posts screen exists. | 1 working day | Engagement | 1
|  | Follow & Unfollow | 80% | Complete | 80% | Complete | Works well. | Done | Engagement | 0
|  | Push Notifications (likes, comments, follows) | 30% | In progress | 40% | In progress | Notification system is set up but not reliably delivering yet. | 5 working days | Engagement | 5
|  | Mention Users (@username) | 40% | In progress | 40% | In progress | Mentioning users in text partially works. | 2 working days | Engagement | 2
|  | Tag Users in Photos | 30% | In progress | 30% | In progress | Photo tagging is not complete. | 3 working days | Engagement | 3
| Messaging (Chat) | One-to-One Chat | 85% | Complete | 85% | Complete | Private chat between two users works well. | Done | Messaging (Chat) | 0
|  | Group Chat | 80% | Complete | 80% | Complete | Group chats work. Small improvements needed. | 1 working day | Messaging (Chat) | 1
|  | Voice Messages | 80% | Complete | 75% | Mostly done | Voice recording and sending works. | 1 working day | Messaging (Chat) | 1
|  | Send Videos in Chat | 60% | Mostly done | 60% | Mostly done | Video sending works but can be slow on large files. | 2 working days | Messaging (Chat) | 2
|  | File Sharing (PDFs, Images, Docs) | 55% | In progress | 55% | In progress | Basic file sharing works. Not all formats supported. | 2 working days | Messaging (Chat) | 2
|  | Disappearing Messages | 0% | Not started | 0% | Not started | Not built. Messages cannot be set to auto-delete. | 4 working days | Messaging (Chat) | 4
|  | Stickers, GIFs & Emojis | 50% | In progress | 40% | In progress | Emojis work. GIFs and sticker packs are incomplete. | 3 working days | Messaging (Chat) | 3
|  | Voice & Video Calling | 0% | Not started | 0% | Not started | Not built yet. This is a key missing feature. | 8 working days | Messaging (Chat) | 8
|  | Group Video Calling | 0% | Not started | 0% | Not started | Not started. | 5 working days | Messaging (Chat) | 5
|  | React to Messages | 60% | Mostly done | 55% | In progress | Message reactions are partially done. | 2 working days | Messaging (Chat) | 2
|  | Edit & Delete Messages | 55% | In progress | 55% | In progress | Delete works. Edit is partial. | 1 working day | Messaging (Chat) | 1
|  | Read Receipts & Typing Indicator | 60% | Mostly done | 60% | Mostly done | Typing indicator works. Read receipts are partial. | 1 working day | Messaging (Chat) | 1
|  | Encrypted Messages | 0% | Not started | 0% | Not started | Not built. Messages are not encrypted. | 6 working days | Messaging (Chat) | 6
|  | Chat Themes & Colours | 0% | Not started | 0% | Not started | Not started. Users cannot customise chat appearance. | Post-Launch | Messaging (Chat) | 0
| Live Streaming | Start a Live Broadcast | 65% | Mostly done | 65% | Mostly done | Hosting a live stream works. | 2 working days | Live Streaming | 2
|  | Invite a Co-Host | 50% | In progress | 55% | In progress | Co-host flow is partial. | 2 working days | Live Streaming | 2
|  | Viewers Join Live as Guest | 50% | In progress | 55% | In progress | Partial. | 2 working days | Live Streaming | 2
|  | Live Chat During Stream | 65% | Mostly done | 65% | Mostly done | Viewers can chat while watching a live stream. | 2 working days | Live Streaming | 2
|  | Send Gift Coins During Live | 55% | In progress | 60% | Mostly done | Coin gifting partially works. | 2 working days | Live Streaming | 2
|  | Live Reactions (floating emoji animations) | 50% | In progress | 50% | In progress | Basic reaction animation is partial. | 2 working days | Live Streaming | 2
|  | Moderation Tools (remove viewers, mute) | 0% | Not started | 20% | Just started | Not in the app. Some backend support only. | 3 working days | Live Streaming | 3
|  | Live Filters & Effects | 0% | Not started | 0% | Not started | Not built. | Post-Launch | Live Streaming | 0
|  | Live Shopping (sell during stream) | 0% | Not started | 0% | Not started | Not started. | Post-Launch | Live Streaming | 0
| Stories (24-hour Content) | Photo Stories | 80% | Complete | 75% | Mostly done | Photo stories work. | Done | Stories (24-hour Content) | 0
|  | Video Stories | 75% | Mostly done | 70% | Mostly done | Video stories work. | 1 working day | Stories (24-hour Content) | 1
|  | Music Stories | 60% | Mostly done | 55% | In progress | Adding music to stories is partially done. | 2 working days | Stories (24-hour Content) | 2
|  | Text Stories | 75% | Mostly done | 70% | Mostly done | Text stories work. | Done | Stories (24-hour Content) | 0
|  | Story Filters | 20% | Just started | 10% | Just started | Very basic. Proper filter selection is not done. | 3 working days | Stories (24-hour Content) | 3
|  | Story Stickers (Polls, Questions, Quizzes) | 0% | Not started | 0% | Not started | Not built. | 4 working days | Stories (24-hour Content) | 4
|  | Mention Users in Stories | 40% | In progress | 35% | In progress | Partial. | 2 working days | Stories (24-hour Content) | 2
|  | Swipe-Up Link (for businesses) | 0% | Not started | 0% | Not started | Not built. | 2 working days | Stories (24-hour Content) | 2
|  | Close Friends Story | 0% | Not started | 0% | Not started | Not started. | 3 working days | Stories (24-hour Content) | 3
|  | Story Highlights on Profile | 0% | Not started | 0% | Not started | Cannot save stories as highlights on profile. | 3 working days | Stories (24-hour Content) | 3
| Groups & Community | Create Public or Private Groups | 60% | Mostly done | 65% | Mostly done | Group creation works. Public/private setting needs refinement. | 2 working days | Groups & Community | 2
|  | Post Inside a Group | 40% | In progress | 50% | In progress | Group posts are partially working. | 3 working days | Groups & Community | 3
|  | Group Admins & Moderators | 20% | Just started | 35% | In progress | Admin role exists. Full moderator tools are not done. | 3 working days | Groups & Community | 3
|  | Group Rules | 0% | Not started | 0% | Not started | Not started. | 2 working days | Groups & Community | 2
|  | Group Events | 0% | Not started | 0% | Not started | Not started. | Post-Launch | Groups & Community | 0
|  | Group Chat | 80% | Complete | 75% | Mostly done | Group messaging works well. | Done | Groups & Community | 0
|  | Approve / Reject Member Requests | 30% | In progress | 40% | In progress | Partial. | 2 working days | Groups & Community | 2
|  | Group Insights (stats for group admin) | 0% | Not started | 0% | Not started | Not built. | 4 working days | Groups & Community | 4
| Pages / Creator / Business | Upgrade Profile to Creator or Business | 0% | Not started | 10% | Just started | Not available in the app. | 5 working days | Pages / Creator / Business | 5
|  | Analytics (views, reach, impressions) | 0% | Not started | 0% | Not started | Not built. No statistics screen for creators. | 6 working days | Pages / Creator / Business | 6
|  | Ads Management Panel | 0% | Not started | 20% | Just started | Not in the app. Basic backend routes only. | 5 working days | Pages / Creator / Business | 5
|  | Monetisation (subscriptions, promotions) | 0% | Not started | 20% | Just started | Not built in the app. | 6 working days | Pages / Creator / Business | 6
|  | Schedule Posts | 0% | Not started | 0% | Not started | Not started. | 3 working days | Pages / Creator / Business | 3
|  | Boost / Promote a Post | 0% | Not started | 10% | Just started | Not in the app. | 3 working days | Pages / Creator / Business | 3
|  | Creator Marketplace (brand deals) | 0% | Not started | 0% | Not started | Not started. | Post-Launch | Pages / Creator / Business | 0
|  | Shop Tab (linked to e-commerce) | 0% | Not started | 0% | Not started | Not started. | Post-Launch | Pages / Creator / Business | 0
| Discovery & Search | Search for Users | 70% | Mostly done | 70% | Mostly done | User search works. | Done | Discovery & Search | 0
|  | Search for Posts & Content | 50% | In progress | 55% | In progress | Basic search works. Full content search needs improvement. | 2 working days | Discovery & Search | 2
|  | Search Hashtags | 40% | In progress | 45% | In progress | Partial. | 2 working days | Discovery & Search | 2
|  | Trending Topics | 20% | Just started | 25% | Just started | Not functional yet. | 3 working days | Discovery & Search | 3
|  | Discover Creators | 30% | In progress | 30% | In progress | Partial suggestions exist. | 2 working days | Discovery & Search | 2
|  | Discover Videos | 50% | In progress | 50% | In progress | Videos discovery screen is partial. | 2 working days | Discovery & Search | 2
|  | Location-Based Discovery | 20% | Just started | 20% | Just started | Not working yet. | 3 working days | Discovery & Search | 3
| Notifications | Notifications for Likes, Comments & Follows | 30% | In progress | 40% | In progress | System is set up but notifications are not reliably delivered. | 4 working days | Notifications | 4
|  | Mention & Tag Notifications | 0% | Not started | 20% | Just started | Not working in the app yet. | 2 working days | Notifications | 2
|  | Story View Notifications | 0% | Not started | 0% | Not started | Not built. | 2 working days | Notifications | 2
|  | Group & Page Notifications | 0% | Not started | 0% | Not started | Not started. | 2 working days | Notifications | 2
|  | Offline Message Notifications | 30% | In progress | 40% | In progress | Users often miss messages when they are offline. | 3 working days | Notifications | 3
|  | Live Stream Invite Notification | 0% | Not started | 0% | Not started | Not built. | 2 working days | Notifications | 2
|  | Custom Notification Settings | 0% | Not started | 0% | Not started | Users cannot choose what notifications they receive. | 3 working days | Notifications | 3
| Safety & Privacy | Block & Report a User | 40% | In progress | 50% | In progress | Buttons exist. Full flow needs finishing. | 2 working days | Safety & Privacy | 2
|  | Report a Post | 30% | In progress | 40% | In progress | Partial. | 1 working day | Safety & Privacy | 1
|  | Hide a Post | 20% | Just started | 25% | Just started | Partial. | 1 working day | Safety & Privacy | 1
|  | Restrict a User (limit interactions) | 0% | Not started | 0% | Not started | Not built. | 2 working days | Safety & Privacy | 2
|  | AI Content Moderation (auto-flag bad content) | 0% | Not started | 0% | Not started | Not started. | Post-Launch | Safety & Privacy | 0
|  | Age Restrictions | 0% | Not started | 0% | Not started | Not built. | 2 working days | Safety & Privacy | 2
|  | Spam Detection | 0% | Not started | 0% | Not started | Not started. | Post-Launch | Safety & Privacy | 0
|  | Family / Kids Mode | 0% | Not started | 0% | Not started | Not started. | Post-Launch | Safety & Privacy | 0
|  | Post Visibility Controls | 0% | Not started | 10% | Just started | Not in the app. | 2 working days | Safety & Privacy | 2
|  | Profile Privacy (public/private) | 0% | Not started | 20% | Just started | Privacy screen not built in the app. | 3 working days | Safety & Privacy | 3
|  | Login Alerts | 0% | Not started | 0% | Not started | Not built. | 2 working days | Safety & Privacy | 2
| Admin Panel | Admin Screen — Manage All Users | 0% | Not started | 40% | In progress | No admin screen in the app. Backend only. | 10 working days | Admin Panel | 10
|  | Admin — Ban & Suspend Accounts | 0% | Not started | 30% | In progress | Backend only. No admin UI. | Done | Admin Panel | 0
|  | Admin — Content Moderation | 0% | Not started | 20% | Just started | Backend only. | Done | Admin Panel | 0
|  | Admin — Manage Ads & Promotions | 0% | Not started | 20% | Just started | Backend only. | Done | Admin Panel | 0
|  | Admin — Analytics Dashboard | 0% | Not started | 10% | Just started | Very early stage. | Done | Admin Panel | 0
|  | Admin — Manage Trending & Hashtags | 0% | Not started | 0% | Not started | Not built. | Done | Admin Panel | 0
|  | Admin — Manage Categories | 0% | Not started | 20% | Just started | Backend only. | Done | Admin Panel | 0
| Monetisation | Creator Earnings System | 0% | Not started | 0% | Not started | Not built. | 5 working days | Monetisation | 5
|  | Gift Coins & Virtual Items | 60% | Mostly done | 65% | Mostly done | Coin purchase and gifting is partially working. | 2 working days | Monetisation | 2
|  | Live Stream Gifting | 55% | In progress | 60% | Mostly done | Coin gifting during live is partial. | 2 working days | Monetisation | 2
|  | Ad Revenue Sharing | 0% | Not started | 0% | Not started | Not started. | Post-Launch | Monetisation | 0
|  | Paid Subscription Tiers | 0% | Not started | 20% | Just started | Not in the app. | 4 working days | Monetisation | 4
|  | Fan Subscriptions | 0% | Not started | 0% | Not started | Not started. | Post-Launch | Monetisation | 0
|  | In-App Coin Purchase | 60% | Mostly done | 65% | Mostly done | Users can buy coin packages via Stripe. | 2 working days | Monetisation | 2
| Advanced / Optional Features | Video Editing Suite (trim, filters, text) | 30% | In progress | 35% | In progress | Basic recording works. Advanced editing still in development. | 7 working days | Advanced / Optional Features | 7
|  | Music Library Integration | 65% | Mostly done | 60% | Mostly done | Music can be added to content. Library is limited. | 2 working days | Advanced / Optional Features | 2
|  | Dark Mode | 0% | Not started | 0% | Not started | Not available. App is light mode only. | 3 working days | Advanced / Optional Features | 3
|  | Multi-Language Support (Arabic / English) | 60% | Mostly done | 0% | Not started | Translation files exist. Not fully applied across the app. | 3 working days | Advanced / Optional Features | 3
|  | AI Content Recommendation Engine | 0% | Not started | 0% | Not started | Not started. Complex feature requiring AI development. | Post-Launch | Advanced / Optional Features | 0
|  | AI Face Filters / AR Effects | 0% | Not started | 0% | Not started | Not started. | Post-Launch | Advanced / Optional Features | 0
|  | AI Auto-Tagging | 0% | Not started | 0% | Not started | Not started. | Post-Launch | Advanced / Optional Features | 0
|  | NSFW / Bad Content Auto-Detection | 0% | Not started | 0% | Not started | Not started. | Post-Launch | Advanced / Optional Features | 0
|  | Nearby Users | 0% | Not started | 0% | Not started | Not started. | Post-Launch | Advanced / Optional Features | 0
|  | Cloud Storage Integration (AWS) | 0% | Not started | 60% | Mostly done | Backend already uses AWS S3 for storing media files. | 2 working days | Advanced / Optional Features | 2
2-MONTH DELIVERY PLAN — SOCIAL MEDIA MODULE
Assumptions
Working days per month (Mon–Sat) |  | 26
Timeline (months) |  | 2
Total working days available |  | 52
Project start date |  | 2026-08-10
Target completion date |  | 2026-10-08
Effort Summary
Total core work (person-days) |  | 295
Features requiring work |  | 109
Features already complete |  | 17
Post-Launch features (excluded from the 2 months) |  | 18
Developers needed in parallel to hit 2 months |  | 6
Work days per developer per month |  | 24.6
Phase Plan by Section
| Section / Category | Phase | Work Days | Share of Total
| User Account & Profile | Month 1 | 15 | 5.085%
| Social Feed (Timeline) | Month 1 | 33 | 11.19%
| Posting & Content Creation | Month 1 | 25 | 8.475%
| Engagement | Month 1 | 18 | 6.102%
| Messaging (Chat) | Month 1 | 36 | 12.2%
| Live Streaming | Month 1 | 15 | 5.085%
| Stories (24-hour Content) | Month 1 | 20 | 6.78%
| Groups & Community | Month 2 | 16 | 5.424%
| Pages / Creator / Business | Month 2 | 28 | 9.492%
| Discovery & Search | Month 2 | 14 | 4.746%
| Notifications | Month 2 | 18 | 6.102%
| Safety & Privacy | Month 2 | 15 | 5.085%
| Admin Panel | Month 2 | 10 | 3.39%
| Monetisation | Month 2 | 15 | 5.085%
| Advanced / Optional Features | Month 2 | 17 | 5.763%
| TOTAL |  | 295 | 100%
Monthly Resourcing
| Phase | Work Days | Developers Needed | Window
| Month 1 | 162 | 7 | 10-Aug-2026 – 08-Sep-2026
| Month 2 | 133 | 6 | 09-Sep-2026 – 08-Oct-2026
| TOTAL | 295 | 7 | 10-Aug-2026 – 08-Oct-2026
Note: Post-Launch items are excluded from the 2-month scope. The 2-month target is achievable only with the parallel developer count shown above; sections are grouped so core social features (feed, posting, engagement, chat, stories, live) land in Month 1 and community, creator, discovery, safety, admin and monetisation land in Month 2.
LEGEND — HOW TO READ THIS SHEET
COLOUR / SYMBOL | PERCENTAGE | WHAT IT MEANS
Complete (Green) | 80% – 100% | This feature is built and working. Ready to use.
Mostly Done (Blue) | 60% – 79% | Built but needs a few finishing touches.
In Progress (Yellow) | 30% – 59% | Development started but not usable yet.
Just Started (Red) | 1% – 29% | Very early stage. Do not expect this to work.
Not Started (Grey) | 0 | Has not been touched yet.
Done (Days column) | 0 days needed | Feature is complete. No more work required.
Post-Launch (Purple) | — | Advanced / optional feature. Planned after October launch.
Number (e.g. "4 working days") | — | Estimated effort to finish this feature.
COLUMN |  | MEANING
Mobile % |  | How complete the feature looks & works on the user's phone.
Backend % |  | How complete the server / data side is (the "engine" behind the app).
Days to Finish |  | Estimated working days a developer needs to complete this feature.
Formulas:
Feature = WORKDAY.INTL([Feature, row above]-1,C155,11)