## Project Status
Super App — Feature Completion & Development Schedule
Social Media • Marketplace • E-Commerce • Food Delivery
Module | Section / Category | Feature | Mobile % | Mobile Status | Backend % | Backend Status | Plain-English Notes | Days to Finish
SOCIAL MEDIA
SOCIAL MEDIA | User Account & Profile | Sign Up & Login (Email, Phone, Google) | 90% | Complete | 90% | Complete | Login and registration fully work across all three methods. | Done
|  | Two-Factor Authentication (extra login security) | 0% | Not started | 0% | Not started | Not built yet. Users have no second step for securing their account. | 3 working days
|  | Profile Picture Upload | 90% | Complete | 90% | Complete | Users can upload and update their profile photo. | Done
|  | Bio, Gender, Location & Birthday | 80% | Complete | 80% | Complete | Profile info screen works. Minor tweaks needed. | 1 working day
|  | User Interests & Hobbies Selection | 80% | Complete | 80% | Complete | Interest selection after sign-up is done. | 1 working day
|  | Follow / Unfollow & Friends System | 80% | Complete | 80% | Complete | Following and followers work. Small polish needed. | 1 working day
|  | Verified Badge (blue tick) | 30% | In progress | 40% | In progress | Badge exists but the full verification process is not complete. | 3 working days
|  | Privacy Settings (public, private, custom) | 0% | Not started | 20% | Just started | Privacy screen does not exist in the app yet. | 4 working days
|  | Block & Report Users | 40% | In progress | 50% | In progress | Buttons exist but the full block/report flow needs finishing. | 2 working days
|  | Profile QR Code | 0% | Not started | 0% | Not started | Not built. Users cannot share their profile via QR code. | Post-Launch
| Social Feed (Timeline) | Scrolling Home Feed | 85% | Complete | 80% | Complete | Main home feed works well. Users can scroll through posts. | Done
|  | Image Posts | 85% | Complete | 80% | Complete | Image posts in the feed are fully working. | Done
|  | Video Posts | 80% | Complete | 75% | Mostly done | Video posts display and play correctly. Minor improvements needed. | 1 working day
|  | Text / Status Posts | 80% | Complete | 75% | Mostly done | Text-only posts work in the feed. | 1 working day
|  | Story Feed (24-hour content) | 75% | Mostly done | 70% | Mostly done | Story bar at top of feed works. | 1 working day
|  | Reels / Short Videos | 80% | Complete | 75% | Mostly done | Short video reels screen works. | 1 working day
|  | Carousels (multiple photos in one post) | 60% | Mostly done | 60% | Mostly done | Multi-image posts exist but the swipe experience needs work. | 3 working days
|  | Polls in Posts | 0% | Not started | 0% | Not started | Not built. Users cannot create polls. | 3 working days
|  | Check-Ins & Location Tagging | 20% | Just started | 20% | Just started | Started but location cannot be tagged on posts yet. | 3 working days
|  | Tag Friends in Posts | 40% | In progress | 40% | In progress | Tagging works partially. Needs completion. | 3 working days
|  | Hashtags | 50% | In progress | 50% | In progress | Hashtags display but searching by hashtag is incomplete. | 2 working days
|  | Trending Section | 20% | Just started | 30% | In progress | Not working yet. No trending topics or content shown. | 4 working days
|  | "For You" Personalised Feed | 0% | Not started | 0% | Not started | Not built. Requires a recommendation system to be developed. | 8 working days
|  | Recommended Users & Posts | 20% | Just started | 20% | Just started | Very basic suggestions. Needs proper logic. | 3 working days
| Posting & Content Creation | Take Photo or Video from App Camera | 85% | Complete | 80% | Complete | Camera capture for posts and stories works. | Done
|  | Camera Filters & Beauty Effects | 25% | Just started | 20% | Just started | Very early stage. Proper AR filters not done yet. | 7 working days
|  | Upload Multiple Photos / Videos | 80% | Complete | 75% | Mostly done | Multiple file upload works. | 1 working day
|  | Save Post as Draft | 30% | In progress | 40% | In progress | Draft saving is unreliable. Needs fixing. | 2 working days
|  | Edit or Delete a Post | 60% | Mostly done | 65% | Mostly done | Delete works. Post editing needs to be completed. | 2 working days
|  | Captions with Emojis | 75% | Mostly done | 70% | Mostly done | Caption input with emoji picker works. | 1 working day
|  | Add Music to Videos or Stories | 65% | Mostly done | 60% | Mostly done | Music can be added. Library is limited. | 2 working days
|  | AI Auto-Caption Suggestion | 0% | Not started | 0% | Not started | Not built. Would require AI integration. | Post-Launch
|  | Start a Live Stream | 65% | Mostly done | 65% | Mostly done | Going live works using the Agora system. | 2 working days
|  | Co-Host a Live Stream | 50% | In progress | 55% | In progress | Co-host invite screen exists but the full flow is incomplete. | 3 working days
|  | Viewers Join Live as a Guest | 50% | In progress | 55% | In progress | Guest joining is partially done. | 3 working days
|  | Send Gift Coins During Live | 55% | In progress | 60% | Mostly done | Coin gifting partially works during live streams. | 2 working days
| Engagement | Like & React to Posts | 80% | Complete | 75% | Mostly done | Likes and emoji reactions on posts work. | 1 working day
|  | Comment on Posts | 80% | Complete | 75% | Mostly done | Users can comment on posts. | 1 working day
|  | Reply to Comments (threaded) | 60% | Mostly done | 60% | Mostly done | Replies partially work. Threading needs improvement. | 2 working days
|  | Heart / Favourite a Comment | 40% | In progress | 45% | In progress | Button exists but saving does not always work. | 1 working day
|  | Share Posts | 60% | Mostly done | 55% | In progress | Sharing within app is partial. Sharing to other apps needs work. | 2 working days
|  | Save / Bookmark Posts | 70% | Mostly done | 70% | Mostly done | Users can save posts. Saved posts screen exists. | 1 working day
|  | Follow & Unfollow | 80% | Complete | 80% | Complete | Works well. | Done
|  | Push Notifications (likes, comments, follows) | 30% | In progress | 40% | In progress | Notification system is set up but not reliably delivering yet. | 5 working days
|  | Mention Users (@username) | 40% | In progress | 40% | In progress | Mentioning users in text partially works. | 2 working days
|  | Tag Users in Photos | 30% | In progress | 30% | In progress | Photo tagging is not complete. | 3 working days
| Messaging (Chat) | One-to-One Chat | 85% | Complete | 85% | Complete | Private chat between two users works well. | Done
|  | Group Chat | 80% | Complete | 80% | Complete | Group chats work. Small improvements needed. | 1 working day
|  | Voice Messages | 80% | Complete | 75% | Mostly done | Voice recording and sending works. | 1 working day
|  | Send Videos in Chat | 60% | Mostly done | 60% | Mostly done | Video sending works but can be slow on large files. | 2 working days
|  | File Sharing (PDFs, Images, Docs) | 55% | In progress | 55% | In progress | Basic file sharing works. Not all formats supported. | 2 working days
|  | Disappearing Messages | 0% | Not started | 0% | Not started | Not built. Messages cannot be set to auto-delete. | 4 working days
|  | Stickers, GIFs & Emojis | 50% | In progress | 40% | In progress | Emojis work. GIFs and sticker packs are incomplete. | 3 working days
|  | Voice & Video Calling | 0% | Not started | 0% | Not started | Not built yet. This is a key missing feature. | 8 working days
|  | Group Video Calling | 0% | Not started | 0% | Not started | Not started. | 5 working days
|  | React to Messages | 60% | Mostly done | 55% | In progress | Message reactions are partially done. | 2 working days
|  | Edit & Delete Messages | 55% | In progress | 55% | In progress | Delete works. Edit is partial. | 1 working day
|  | Read Receipts & Typing Indicator | 60% | Mostly done | 60% | Mostly done | Typing indicator works. Read receipts are partial. | 1 working day
|  | Encrypted Messages | 0% | Not started | 0% | Not started | Not built. Messages are not encrypted. | 6 working days
|  | Chat Themes & Colours | 0% | Not started | 0% | Not started | Not started. Users cannot customise chat appearance. | Post-Launch
| Live Streaming | Start a Live Broadcast | 65% | Mostly done | 65% | Mostly done | Hosting a live stream works. | 2 working days
|  | Invite a Co-Host | 50% | In progress | 55% | In progress | Co-host flow is partial. | 2 working days
|  | Viewers Join Live as Guest | 50% | In progress | 55% | In progress | Partial. | 2 working days
|  | Live Chat During Stream | 65% | Mostly done | 65% | Mostly done | Viewers can chat while watching a live stream. | 2 working days
|  | Send Gift Coins During Live | 55% | In progress | 60% | Mostly done | Coin gifting partially works. | 2 working days
|  | Live Reactions (floating emoji animations) | 50% | In progress | 50% | In progress | Basic reaction animation is partial. | 2 working days
|  | Moderation Tools (remove viewers, mute) | 0% | Not started | 20% | Just started | Not in the app. Some backend support only. | 3 working days
|  | Live Filters & Effects | 0% | Not started | 0% | Not started | Not built. | Post-Launch
|  | Live Shopping (sell during stream) | 0% | Not started | 0% | Not started | Not started. | Post-Launch
| Stories (24-hour Content) | Photo Stories | 80% | Complete | 75% | Mostly done | Photo stories work. | Done
|  | Video Stories | 75% | Mostly done | 70% | Mostly done | Video stories work. | 1 working day
|  | Music Stories | 60% | Mostly done | 55% | In progress | Adding music to stories is partially done. | 2 working days
|  | Text Stories | 75% | Mostly done | 70% | Mostly done | Text stories work. | Done
|  | Story Filters | 20% | Just started | 10% | Just started | Very basic. Proper filter selection is not done. | 3 working days
|  | Story Stickers (Polls, Questions, Quizzes) | 0% | Not started | 0% | Not started | Not built. | 4 working days
|  | Mention Users in Stories | 40% | In progress | 35% | In progress | Partial. | 2 working days
|  | Swipe-Up Link (for businesses) | 0% | Not started | 0% | Not started | Not built. | 2 working days
|  | Close Friends Story | 0% | Not started | 0% | Not started | Not started. | 3 working days
|  | Story Highlights on Profile | 0% | Not started | 0% | Not started | Cannot save stories as highlights on profile. | 3 working days
| Groups & Community | Create Public or Private Groups | 60% | Mostly done | 65% | Mostly done | Group creation works. Public/private setting needs refinement. | 2 working days
|  | Post Inside a Group | 40% | In progress | 50% | In progress | Group posts are partially working. | 3 working days
|  | Group Admins & Moderators | 20% | Just started | 35% | In progress | Admin role exists. Full moderator tools are not done. | 3 working days
|  | Group Rules | 0% | Not started | 0% | Not started | Not started. | 2 working days
|  | Group Events | 0% | Not started | 0% | Not started | Not started. | Post-Launch
|  | Group Chat | 80% | Complete | 75% | Mostly done | Group messaging works well. | Done
|  | Approve / Reject Member Requests | 30% | In progress | 40% | In progress | Partial. | 2 working days
|  | Group Insights (stats for group admin) | 0% | Not started | 0% | Not started | Not built. | 4 working days
| Pages / Creator / Business | Upgrade Profile to Creator or Business | 0% | Not started | 10% | Just started | Not available in the app. | 5 working days
|  | Analytics (views, reach, impressions) | 0% | Not started | 0% | Not started | Not built. No statistics screen for creators. | 6 working days
|  | Ads Management Panel | 0% | Not started | 20% | Just started | Not in the app. Basic backend routes only. | 5 working days
|  | Monetisation (subscriptions, promotions) | 0% | Not started | 20% | Just started | Not built in the app. | 6 working days
|  | Schedule Posts | 0% | Not started | 0% | Not started | Not started. | 3 working days
|  | Boost / Promote a Post | 0% | Not started | 10% | Just started | Not in the app. | 3 working days
|  | Creator Marketplace (brand deals) | 0% | Not started | 0% | Not started | Not started. | Post-Launch
|  | Shop Tab (linked to e-commerce) | 0% | Not started | 0% | Not started | Not started. | Post-Launch
| Discovery & Search | Search for Users | 70% | Mostly done | 70% | Mostly done | User search works. | Done
|  | Search for Posts & Content | 50% | In progress | 55% | In progress | Basic search works. Full content search needs improvement. | 2 working days
|  | Search Hashtags | 40% | In progress | 45% | In progress | Partial. | 2 working days
|  | Trending Topics | 20% | Just started | 25% | Just started | Not functional yet. | 3 working days
|  | Discover Creators | 30% | In progress | 30% | In progress | Partial suggestions exist. | 2 working days
|  | Discover Videos | 50% | In progress | 50% | In progress | Videos discovery screen is partial. | 2 working days
|  | Location-Based Discovery | 20% | Just started | 20% | Just started | Not working yet. | 3 working days
| Notifications | Notifications for Likes, Comments & Follows | 30% | In progress | 40% | In progress | System is set up but notifications are not reliably delivered. | 4 working days
|  | Mention & Tag Notifications | 0% | Not started | 20% | Just started | Not working in the app yet. | 2 working days
|  | Story View Notifications | 0% | Not started | 0% | Not started | Not built. | 2 working days
|  | Group & Page Notifications | 0% | Not started | 0% | Not started | Not started. | 2 working days
|  | Offline Message Notifications | 30% | In progress | 40% | In progress | Users often miss messages when they are offline. | 3 working days
|  | Live Stream Invite Notification | 0% | Not started | 0% | Not started | Not built. | 2 working days
|  | Custom Notification Settings | 0% | Not started | 0% | Not started | Users cannot choose what notifications they receive. | 3 working days
| Safety & Privacy | Block & Report a User | 40% | In progress | 50% | In progress | Buttons exist. Full flow needs finishing. | 2 working days
|  | Report a Post | 30% | In progress | 40% | In progress | Partial. | 1 working day
|  | Hide a Post | 20% | Just started | 25% | Just started | Partial. | 1 working day
|  | Restrict a User (limit interactions) | 0% | Not started | 0% | Not started | Not built. | 2 working days
|  | AI Content Moderation (auto-flag bad content) | 0% | Not started | 0% | Not started | Not started. | Post-Launch
|  | Age Restrictions | 0% | Not started | 0% | Not started | Not built. | 2 working days
|  | Spam Detection | 0% | Not started | 0% | Not started | Not started. | Post-Launch
|  | Family / Kids Mode | 0% | Not started | 0% | Not started | Not started. | Post-Launch
|  | Post Visibility Controls | 0% | Not started | 10% | Just started | Not in the app. | 2 working days
|  | Profile Privacy (public/private) | 0% | Not started | 20% | Just started | Privacy screen not built in the app. | 3 working days
|  | Login Alerts | 0% | Not started | 0% | Not started | Not built. | 2 working days
| Admin Panel | Admin Screen — Manage All Users | 0% | Not started | 40% | In progress | No admin screen in the app. Backend only. | 10 working days
|  | Admin — Ban & Suspend Accounts | 0% | Not started | 30% | In progress | Backend only. No admin UI. | Done
|  | Admin — Content Moderation | 0% | Not started | 20% | Just started | Backend only. | Done
|  | Admin — Manage Ads & Promotions | 0% | Not started | 20% | Just started | Backend only. | Done
|  | Admin — Analytics Dashboard | 0% | Not started | 10% | Just started | Very early stage. | Done
|  | Admin — Manage Trending & Hashtags | 0% | Not started | 0% | Not started | Not built. | Done
|  | Admin — Manage Categories | 0% | Not started | 20% | Just started | Backend only. | Done
| Monetisation | Creator Earnings System | 0% | Not started | 0% | Not started | Not built. | 5 working days
|  | Gift Coins & Virtual Items | 60% | Mostly done | 65% | Mostly done | Coin purchase and gifting is partially working. | 2 working days
|  | Live Stream Gifting | 55% | In progress | 60% | Mostly done | Coin gifting during live is partial. | 2 working days
|  | Ad Revenue Sharing | 0% | Not started | 0% | Not started | Not started. | Post-Launch
|  | Paid Subscription Tiers | 0% | Not started | 20% | Just started | Not in the app. | 4 working days
|  | Fan Subscriptions | 0% | Not started | 0% | Not started | Not started. | Post-Launch
|  | In-App Coin Purchase | 60% | Mostly done | 65% | Mostly done | Users can buy coin packages via Stripe. | 2 working days
| Advanced / Optional Features | Video Editing Suite (trim, filters, text) | 30% | In progress | 35% | In progress | Basic recording works. Advanced editing still in development. | 7 working days
|  | Music Library Integration | 65% | Mostly done | 60% | Mostly done | Music can be added to content. Library is limited. | 2 working days
|  | Dark Mode | 0% | Not started | 0% | Not started | Not available. App is light mode only. | 3 working days
|  | Multi-Language Support (Arabic / English) | 60% | Mostly done | 0% | Not started | Translation files exist. Not fully applied across the app. | 3 working days
|  | AI Content Recommendation Engine | 0% | Not started | 0% | Not started | Not started. Complex feature requiring AI development. | Post-Launch
|  | AI Face Filters / AR Effects | 0% | Not started | 0% | Not started | Not started. | Post-Launch
|  | AI Auto-Tagging | 0% | Not started | 0% | Not started | Not started. | Post-Launch
|  | NSFW / Bad Content Auto-Detection | 0% | Not started | 0% | Not started | Not started. | Post-Launch
|  | Nearby Users | 0% | Not started | 0% | Not started | Not started. | Post-Launch
|  | Cloud Storage Integration (AWS) | 0% | Not started | 60% | Mostly done | Backend already uses AWS S3 for storing media files. | 2 working days
MARKETPLACE
MARKETPLACE | Property | Browse Properties (Buy / Rent / Sell) | 75% | Mostly done | 70% | Mostly done | Property listings, filters, and details all work. | Done
|  | Location & Price Filters | 70% | Mostly done | 65% | Mostly done | Filters for location, price, and amenities work. | 1 working day
|  | Property Photos & Videos | 75% | Mostly done | 70% | Mostly done | Multiple photos/videos can be uploaded per listing. | Done
|  | Post / Edit / Delete Property Ad | 65% | Mostly done | 70% | Mostly done | Sellers can manage their listings. | 2 working days
|  | Save / Draft Ads | 50% | In progress | 55% | In progress | Draft saving partially works. | 1 working day
|  | Ad Insights (views, clicks stats) | 55% | In progress | 50% | In progress | Basic stats screen exists but data is limited. | 2 working days
|  | Map-Based Property Search | 65% | Mostly done | 55% | In progress | Map view is partially done. | 2 working days
|  | Estate Agent Profiles | 50% | In progress | 55% | In progress | Agent profiles partially built. | 2 working days
|  | Favourite Properties | 65% | Mostly done | 60% | Mostly done | Users can save favourite listings. | 1 working day
| Motors (Vehicles) | Browse Cars & Vehicles | 70% | Mostly done | 65% | Mostly done | Vehicle listings work. | Done
|  | Make / Model / Year Filters | 65% | Mostly done | 60% | Mostly done | Basic vehicle filters work. Advanced filters need improvement. | 2 working days
|  | Post a Vehicle Ad with Photos | 65% | Mostly done | 65% | Mostly done | Sellers can create vehicle listings. | 2 working days
|  | Pay to Feature / Promote Ad | 60% | Mostly done | 60% | Mostly done | Payment for listing promotions is partial. | 2 working days
| Classifieds (General Goods) | Browse General Item Listings | 60% | Mostly done | 55% | In progress | Classifieds listings work for furniture, electronics, etc. | 2 working days
|  | Search & Filter Items | 55% | In progress | 55% | In progress | Search and filters work. | 2 working days
|  | Post a Classified Ad | 55% | In progress | 55% | In progress | Users can post general item ads. | 2 working days
|  | Classified Item Details Page | 60% | Mostly done | 55% | In progress | Full details view works. | 1 working day
| Jobs | Browse Job Listings | 65% | Mostly done | 65% | Mostly done | Job board works. Users can browse available jobs. | 1 working day
|  | Job Search & Category Filter | 65% | Mostly done | 60% | Mostly done | Search and categories work. | 1 working day
|  | Post a Job (Employer) | 60% | Mostly done | 60% | Mostly done | Employers can post jobs. | 2 working days
|  | CV Builder & Upload | 40% | In progress | 40% | In progress | CV builder exists but upload logic is incomplete. | 2 working days
|  | Apply for a Job (Job Seeker) | 35% | In progress | 40% | In progress | Broken — the application flow does not complete properly. | 3 working days
| Services | Browse Service Listings (plumbing, tutoring, etc.) | 0% | Not started | 0% | Not started | Not built. Services marketplace does not exist yet. | 8 working days
|  | Post a Service | 0% | Not started | 0% | Not started | Not started. | Done
|  | Book / Contact a Service Provider | 0% | Not started | 0% | Not started | Not started. | Done
| Community / Misc | Community Posts & Giveaways | 0% | Not started | 0% | Not started | Not built. | 4 working days
|  | Wanted Ads | 0% | Not started | 0% | Not started | Not started. | Done
| General Marketplace Features | In-App Buyer–Seller Chat | 70% | Mostly done | 70% | Mostly done | Buyers and sellers can chat directly. | 1 working day
|  | Ratings & Reviews for Sellers | 35% | In progress | 40% | In progress | Review screen exists but is not fully working. | 3 working days
|  | Verified Seller Accounts | 30% | In progress | 40% | In progress | Verification badge partially done. | 3 working days
|  | Featured / Premium Listings | 55% | In progress | 55% | In progress | Paid featured listings partially working. | 2 working days
|  | Multiple Photo Upload per Listing | 70% | Mostly done | 70% | Mostly done | Sellers can upload multiple photos. | Done
E-COMMERCE
E-COMMERCE | Customer App (Buyer) | Login (Email, Phone, OTP, Google) | 85% | Complete | 85% | Complete | All login methods work. | Done
|  | Home Page (Banners, Categories, Trending) | 55% | In progress | 55% | In progress | Home page exists but flash sales and personalised sections are incomplete. | 3 working days
|  | Browse Products by Category & Filter | 70% | Mostly done | 65% | Mostly done | Product browsing and filters work. | 1 working day
|  | Product Search | 55% | In progress | 55% | In progress | Search works but auto-suggestions need improvement. | 2 working days
|  | Product Details Page (images, price, variants) | 75% | Mostly done | 70% | Mostly done | Full product details display correctly. | 1 working day
|  | Add to Cart & Buy Now | 80% | Complete | 75% | Mostly done | Cart and quick-buy work. | Done
|  | Apply Promo / Coupon Codes | 65% | Mostly done | 65% | Mostly done | Coupon codes work at checkout. | 1 working day
|  | Multiple Payment Methods (Card, Google Pay) | 75% | Mostly done | 70% | Mostly done | Stripe, card, and Google Pay all work. | Done
|  | Order History | 70% | Mostly done | 70% | Mostly done | Users can view their past orders. | 1 working day
|  | Order Tracking (live status updates) | 55% | In progress | 55% | In progress | Order status exists but real-time live tracking is partial. | 3 working days
|  | Cancel or Return a Product | 30% | In progress | 40% | In progress | Return request screen started but not complete. | 3 working days
|  | Refund System | 20% | Just started | 35% | In progress | Very basic. Refund processing not fully built. | 4 working days
|  | Wishlist | 40% | In progress | 45% | In progress | Wishlist exists but some features are missing. | 2 working days
|  | Chat with Seller | 60% | Mostly done | 60% | Mostly done | In-app buyer–seller chat works. | 1 working day
|  | Order Push Notifications | 30% | In progress | 40% | In progress | Notifications often do not arrive. | 3 working days
|  | Flash Sales | 0% | Not started | 0% | Not started | Not built. | 3 working days
|  | Loyalty Points & Wallet | 55% | In progress | 55% | In progress | Coin and wallet system is partially built. | 2 working days
| Vendor App (Seller) | Vendor Registration & Login | 0% | Not started | 60% | Mostly done | No seller screen in the app. Backend can register vendors. | 5 working days
|  | Vendor Dashboard (sales, orders, earnings) | 0% | Not started | 40% | In progress | Backend only. No mobile screen for sellers. | 4 working days
|  | Add / Edit / Delete Products | 0% | Not started | 65% | Mostly done | Backend supports this. No seller app screen. | 4 working days
|  | Vendor Order Management | 0% | Not started | 55% | In progress | Backend only. | 3 working days
|  | Store Management (logo, banner, description) | 0% | Not started | 40% | In progress | Backend only. | 3 working days
|  | Vendor Earnings & Payout | 0% | Not started | 35% | In progress | Backend only. | 4 working days
|  | Vendor Chat with Customers | 0% | Not started | 45% | In progress | No dedicated seller chat screen. | 2 working days
| Delivery Boy App | Delivery Rider Login & Registration | 0% | Not started | 35% | In progress | Backend supports riders. No rider mobile screen. | 3 working days
|  | Rider Dashboard (assigned orders, map) | 0% | Not started | 30% | In progress | Backend only. No rider app screen. | 4 working days
|  | Accept / Reject Delivery | 0% | Not started | 30% | In progress | Backend only. | 3 working days
|  | Mark Order as Delivered | 0% | Not started | 20% | Just started | Backend only. | 2 working days
|  | Rider Earnings Report | 0% | Not started | 20% | Just started | Backend only. | 2 working days
| Admin Panel (E-Commerce) | Admin Dashboard (users, sales, revenue) | 0% | Not started | 30% | In progress | No admin app. Basic backend data only. | 3 working days
|  | Approve / Manage Vendors | 0% | Not started | 35% | In progress | Backend only. | 3 working days
|  | Approve / Reject Products | 0% | Not started | 35% | In progress | Backend only. | 3 working days
|  | Full Order Control (cancel, override) | 0% | Not started | 35% | In progress | Backend only. | 2 working days
|  | Manage Promotions & Banners | 0% | Not started | 30% | In progress | Backend only. | 3 working days
|  | Reports & Analytics | 0% | Not started | 20% | Just started | Very early stage. | 4 working days
|  | Vendor Commission Management | 0% | Not started | 30% | In progress | Basic commission in backend. | 3 working days
|  | Vendor Payout Processing | 0% | Not started | 30% | In progress | Backend only. | 2 working days
| Multi-Vendor Features | Product Reviews & Seller Ratings | 40% | In progress | 40% | In progress | Review screen exists. Rating totals need work. | 2 working days
|  | Return & Refund Process | 20% | Just started | 35% | In progress | Partial on both sides. | 2 working days
|  | Third-Party Delivery Integration (DHL, Aramex) | 0% | Not started | 0% | Not started | Not started. | Post-Launch
|  | Automated Commission Deduction | 0% | Not started | 30% | In progress | Backend only. | 2 working days
FOOD DELIVERY
FOOD DELIVERY | Food Ordering | Browse Restaurants & Menus | 70% | Mostly done | 65% | Mostly done | Restaurant listings and menu browsing work. | Done
|  | Cuisine & Category Filters | 65% | Mostly done | 60% | Mostly done | Filter by cuisine type works. | 1 working day
|  | Restaurant Search | 65% | Mostly done | 60% | Mostly done | Search works. | 1 working day
|  | Add Items to Cart & Place Order | 70% | Mostly done | 65% | Mostly done | Food cart and order placement work. | 1 working day
|  | Promo Codes & Discounts | 60% | Mostly done | 60% | Mostly done | Vouchers can be applied at checkout. | 1 working day
|  | Multiple Payment Methods | 70% | Mostly done | 65% | Mostly done | Card and cashless payments work. | Done
|  | Order History | 60% | Mostly done | 55% | In progress | Past food orders can be viewed. | 2 working days
| Order Tracking & Delivery | Live Order Tracking (see rider on map) | 40% | In progress | 40% | In progress | Tracking screen exists but live rider location not fully implemented. | 5 working days
|  | Estimated Delivery Time | 30% | In progress | 30% | In progress | Estimate display is partial. | 2 working days
|  | Pickup Option (collect without delivery fee) | 30% | In progress | 30% | In progress | Partial. | 2 working days
|  | Favourite Orders & Reorder | 30% | In progress | 30% | In progress | Not fully done. | 2 working days
|  | Delivery Fee Calculation (free/standard/priority) | 0% | Not started | 0% | Not started | Broken. Fee calculation and delivery option selection not working. | 3 working days
| Ratings & Support | Rate a Restaurant or Dish | 30% | In progress | 35% | In progress | Review screen started but not complete. | 2 working days
|  | In-App Customer Support Chat | 0% | Not started | 20% | Just started | Not in the app. | 2 working days
|  | Personalised Food Recommendations | 0% | Not started | 0% | Not started | Not started. | Post-Launch
|  | Membership / Subscription (e.g. free delivery pass) | 0% | Not started | 0% | Not started | Not started. | Post-Launch
| Delivery Rider App | Rider Registration & Login | 0% | Not started | 25% | Just started | Backend supports riders. No rider mobile screen. | 4 working days
|  | Rider Dashboard (assigned orders, map) | 0% | Not started | 25% | Just started | Backend only. No rider app screen. | 4 working days
|  | Accept Orders & Mark as Delivered | 0% | Not started | 25% | Just started | Backend only. | 3 working days
|  | Rider Earnings Report | 0% | Not started | 20% | Just started | Backend only. | 2 working days
SCHEDULE SUMMARY
Total Feature-Days (core work) |  | 484 person-days ( 4 months and 2 weeks ) |  | This is the total amount of work across all features that need to be finished (excluding Post-Launch items).
Estimated Calendar Days Needed |  | 97 working days
Start Date |  | -----
Estimated Completion Date |  | ----
Post-Launch Features (deferred) |  | 21 features |  | These are advanced / optional features (AI, AR, live shopping, etc.) that are NOT included in the October deadline. They can be built after launch.
Features Already Complete |  | 29 features |  | These required no further work.

## Legend
COLOUR / SYMBOL | PERCENTAGE | WHAT IT MEANS
Complete (Green) | 80% – 100% | This feature is built and working. Ready to use.
Mostly Done (Blue) | 60% – 79% | Built but needs a few finishing touches.
In Progress (Yellow) | 30% – 59% | Development started but not usable yet.
Just Started (Red) | 1% – 29% | Very early stage. Do not expect this to work.
Not Started (Grey) | 0 | Has not been touched yet.
Done (Days column) | 0 days needed | Feature is complete. No more work required.
Post-Launch (Purple) | — | Advanced / optional feature. Planned after October launch.
Number (e.g. "4 working days") | — | Estimated effort to finish this feature.
COLUMN |  | MEANING
Mobile % |  | How complete the feature looks & works on the user's phone.
Backend % |  | How complete the server / data side is (the "engine" behind the app).
Days to Finish |  | Estimated working days a developer needs to complete this feature.